## Sprint 1
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 90 | 162 | 157 | 152 | 130 | 115 | 99 | 90 | 78 | 60 | 47 | 30
Architecture diagram | Architecture diagram | Rinku | 10 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 0
DB design | DB design | Apoorva | 12 | 0 | 0 | 1 | 3 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0
Frontend baseline | Frontend baseline | Junie | 20 | 0 | 0 | 8 | 0 | 3 | 0 | 1 | 0 | 0 | 2 | 3 | 0 | 3 | 0
Backend baseline | Backend baseline | Ananya | 20 | 0 | 0 | 4 | 3 | 0 | 0 | 3 | 4 | 4 | 3 | 0 | 0 | 0 | 0
Wireframe for login, registration, landing and listing | Wireframe for login, registration, landing and listing | Apoorva/Ananya | 12 | 0 | 0 | 0 | 1 | 4 | 0 | 2 | 2 | 0 | 1 | 2 | 0 | 0 | 0
Unit Testing Framework | Unit Testing Framework | Junie | 6 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
UI routing protection added | UI routing protection added | Apoorva | 10 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 0
|  |  | Total | 90 | 90 | 73 | 63 | 52 | 48 | 42 | 30 | 23 | 12 | 2 | -15 | -27 | -34
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
Team:
Apoorva | 9 hours / Week
Ananya | 9 hours / Week
Junie | 9 hours / Week
Rinku | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint 2
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2025-03-12 | ##### | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 68 | 62 | 54 | 47 | 41 | 38 | 35 | 32 | 27.5 | 19
hotel search component | restaurant search component | Apoorva | 8 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 2 | 1.5 | 1 | 0 | 0 | 0
Backend baseline | db setup | Ananya | 12 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0
User Registration | User Registration | Apoorva | 10 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 0
Wireframe Hotel Booking and booking summary UI | Wireframe Hotel Booking and booking summary UI | Ananya | 6 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Admin Login | Admin Login | Rinku | 8 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0
Admin wireframe | Admin wireframe | Rinku | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
Restuarant Manager wireframe | Restuarant Manager wireframe | Junie | 6 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
Restaurant Manager Login | Restuaran tManager login | Junie | 10 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0
Backend for Login | Backend for Login | Apoorva | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0
|  |  | Total | 68 | 62 | 54 | 47 | 41 | 38 | 35 | 32 | 27 | 19 | 11 | 8 | 2 | 0
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
72
Team:
Apoorva | 9 hours / Week
Ananya | 9 hours / Week
Rinku | 9 hours / Week
Junie | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint 3
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2025-03-26 | ##### | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 66 | 52 | 34 | 23 | 19 | 11 | 5 | -5 | -12 | -30 | 8 | 5 | 5
Backend service for reservation | Backend service for registration | Ananya | 7 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0
Registraion summary frontend | Registration summary frontend | Ananya | 7 | 3 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 0
My reservations Change/ Cancel reservation Wireframes | My Bookings Change/ Cancel Booking Wireframes | Apoorva | 3 | 0 | 2 | 0 | 2 | 0 | 4 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0
Reservations api | Reservations api | Apoorva | 6 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0
Ec2 autoscaling group | Ec2 autoscaling group | Junie | 6 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0
Wireframe for review | wireframe for review | Ananya | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Admin Restaurant listing api | Admin restaurants api | Rinku | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
Code Refactoration | Code Refactoration | Rinku | 8 | 2 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 1
Persistance for JWT | Redux Persistance Introduced | Apoorva | 7 | 1 | 0 | 2 | 1 | 0 | 1 | 1 | 2 | 0 | 2 | 0 | 0 | 1 | 0
Frontend Integration - Sprint 1 | Frontend Integration - Sprint 1 | Junie | 6 | 1 | 0 | 2 | 2 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 1 | 2 | 2
Admin Dashboard | Introduced AWS Cognito to the System | Rinku | 3 | 0 | 0 | 3 | 1 | 2 | 0 | 2 | 1 | 1 | 2 | 1 | 1 | 0 | 0
Restaurant Manager Add restaurant | Restaurant manger | Junie | 4 | 0 | 2 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 3 | 0 | 0 | 2
|  |  | Total | 65 | 53 | 34 | 23 | 19 | 11 | 5 | -5 | -12 | -30 | -41 | -49 | -54 | -59
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
0
Team:
Apoorva | 9 hours / Week
Ananya | 9 hours / Week
Rinku | 9 hours / Week
Junie | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint 4
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2025-04-09 | ##### | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 64 | 57 | 42 | 32 | 23 | 20 | 16 | 10 | 3 | -4
Front end UI Search and Navigation | Front end UI Search and Navigation | Apoorva | 8 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0
Integrate backend and front-end and google maps | Front end backend and google maps | Apoorva | 8 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Integrated the frontend and backend | created api for reviews | Ananya | 7 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
backend services for Flask and | Integrated the frontend and backend | Ananya | 7 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0
UI for photo uploads (React | UI for photo uploads (React | Junie | 7 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Flask endpoint placeholders for photo upload | Flask endpoint placeholders for photo upload | Junie | 7 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Integrated support for restaurant descriptions | ntegrated support for restaurant descriptions | Junie | 5 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0
Frontend Integration - Sprint - 2 | Frontend Integration - Sprint - 2 | Apoorva/Ananya | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Connected "View", "Approve", "Delete" actions | Connected "View", "Approve", "Delete" actions | Rinku | 8 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 2 | 1 | 2 | 0 | 1 | 0 | 0
Styled admin dashboard | Styled admin dashboard | Rinku | 7 | 2 | 0 | 1 | 2 | 1 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0
integration testing | integration testing | Rinku | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 64 | 57 | 42 | 32 | 23 | 20 | 16 | 10 | 3 | -4 | -11 | -16 | -20 | -23
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
0
Team:
Apoorva | 9 hours / Week
Ananya | 9 hours / Week
Rinku | 9 hours / Week
Junie | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint 5
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2025-04-23 | ##### | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 63 | 54 | 46 | 39 | 35 | 31 | 27 | 18 | 7 | 0
Restaurant manager and admin integration | Restaurant manager and admin integration | Rinku/Junie | 6 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0
Front end polish | Front end polish | Junie | 7 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
document API | document API | Junie | 7 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
Cleaned up admin modals and image rendering | Cleaned up admin modals and image rendering | Rinku | 7 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Admin dashboard | Admin Dashboard | Rinku | 7 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0
Tested application | Tested application | Ananya | 8 | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0
Deployed application | Deployed application | Ananya | 7 | 1 | 1.5 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0
Merge conflict resolve | Merge conflict resolve | Apoorva | 8 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bug fixes | Bug fixes | Apoorva | 6 | 1 | 0 | 2 | 1 | 0 | 0 | 2 | 1 | 1 | 0 | 2 | 1 | 2 | 0
Customer API Integration | Customer API Integration | Apoorva/Ananya | 8 | 1 | 0 | 2 | 1 | 0 | 2 | 0 | 1 | 3 | 0 | 1 | 1 | 1 | 2
|  |  | Total | 63 | 54 | 46 | 39 | 35 | 31 | 27 | 18 | 7 | 0 | -5 | -2 | -5 | -7
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
0
Team:
Ananya | 9 hours / Week
Apoorva | 9 hours / Week
Junie | 9 hours / Week
Rinku | 9 hours / Week
Total Available Hours During Sprint: | 72